## Sheet1
Task Name | Description | Estimated Duration | Resource | Start Time | End Time
ID card | Print directly from web-based | 2 Days | Panha
Certificate | Just correct the format of certificate and make sure the notification work properly with status | 1 Days | Panha
E-Cert | Reminding notification | 2 Days | Panha
SOA Report | Course result in attendance for Gov | 2 Days | Panha
Attendance | Scanning machine |  | Panha
E-assessment | Random question | 3 Days | Panha
Sale Order in History | Be able to issue sales order before the course | 3 Days | Reaksmey
CSV combine in History |  | 4 Days | Reaksmey
No charge for retake student | Will need to have a field discount for each candidate who retake the class within one month | 2 Days | Reaksmey
Customer's discount | Some existing customers have special price for some courses | 2 Days | Reaksmey
Person in charge(invoice) | Need to add Person in charge for Invoice under corporate profile | 4 hours | Reaksmey
Interim letter | Interim letter is generated only WDA not for Safety course and issue only the customer who paid already | 2 Days | Reaksmey
Trainee report | report trainee by course or date range | 2 Days | Panha
Trainer report |  | 1 Days | Panha
Sale report |  | 2 Days | Panha
User(Corporate & Individual) report |  | 2 Days | Panha
Calculate Trainer's salary |  | 3 Days | Panha
Survey |  | 3 Days | Panha
Print log |  | 4 Days | Panha
Add or remove field for each user profile |  | 1 Days | Panha
Update field in Course detail |  | 1 Days | Panha
Add link WTF Funding for trainee | Add a link for WTF Funding under profile if the trainee is funding status | 4 hours | Reaksmey
Update invoice format |  | 1 Days | Reaksmey